## Project Planner
Sprint 2 - Accuracy
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | STAFF MEMBER(S) | PLAN START (Hours) | PLAN DURATION (Hours) | ACTUAL START (Hours) | ACTUAL DURATION (Hours) | PERCENT COMPLETE | HOURS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Develop a plan (Gantt chart) | Aidan, Jason, Bryan | 1 | 2 | 1 | 1 | 100% | bar: HOURS 1 to HOURS 2
Build requirements table | Aidan, Jason, Bryan | 3 | 2 | 2 | 2 | 100% | bar: HOURS 2 to HOURS 4
Requirements signoff table | Aidan, Jason, Bryan | 5 | 1 | 4 | 1 | 100% | bar: HOURS 4 to HOURS 5
Create an Algorithm | Jason | 6 | 2 | 5 | 1 | 100% | bar: HOURS 5 to HOURS 7
Create a Flowchart | Bryan | 8 | 1 | 6 | 1 | 100% | bar: HOURS 6; HOURS 8
Create Block Code | Jason | 9 | 3 | 7 | 4 | 100% | bar: HOURS 7 to HOURS 11
Sensor data diagram | Aidan | 12 | 1 | 11 | 1 | 100% | bar: HOURS 11 to HOURS 12
Test Table | Aidan, Jason, Bryan | 13 | 2 | 12 | 1 | 100% | bar: HOURS 12 to HOURS 14
Staffing Plan | Aidan, Jason, Bryan | 15 | 1 | 13 | 1 | 100% | bar: HOURS 13; HOURS 15
System Design Document | Aidan, Jason, Bryan | 16 | 6 | 14 | 4 | 100% | bar: HOURS 14 to HOURS 21
Robot Video | Bryan | 22 | 1 | 18 | 1 | 100% | bar: HOURS 18; HOURS 22
Github Repository | Jason | 23 | 2 | 19 | 1 | 100% | bar: HOURS 19; HOURS 23 to HOURS 24
Robot Performance Test | Aidan, Jason, Bryan | 25 | 2 | 20 | 1 | 100% | bar: HOURS 20; HOURS 25 to HOURS 26